ANNEX 1

ROADMAPS TO IMPLEMENT EACH ACTION

Implementation of the EUSDR Priority Area 6 to preserve biodiversity, landscapes and the quality of air and soils

30 June 2012

ROADMAPS TO IMPLEMENT EACH ACTION

Action 1: “To contribute to the 2050 EU vision and 2020 EU target for biodiversity”

Action 6.1 “To contribute to the 2050 EU vision and 2020 EU target for biodiversity”

In 2010, EU Heads of State and Government at the Spring European Council adopted a long-term vision and a headline target for European biodiversity beyond 2010. The European Commission is currently developing a strategy outlining the way to achieving the 2020 biodiversity target. Actions under the Danube Strategy will fully contribute to the implementation of the post-2010 EU biodiversity strategy to halt biodiversity loss and ecosystems services' degradation and to restore them in so far as feasible.

Milestone n°6.011: Assessment made for EUSRD region on update and revision of national biodiversity strategic documents in line with CBD Strategic Plan for Biodiversity 2011-2020 and Aichi Biodiversity Targets

Work/Rationale: In decision X/2, the tenth meeting of the Conference of the Parties to the CBD, adopted a revised and updated Strategic Plan for Biodiversity, including the Aichi Biodiversity Targets, for the 2011-2020 period with the country obligation to translate this overarching international framework into national biodiversity strategies and action plans by COP 12.

Output: Assessment prepared on update and revision of national biodiversity strategic documents

Countries involved: Danube Region Countries

Deadline: I. quarter 2015 (after the CBD COP 12)

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020

- Relation to EU Biodiversity 2020 Strategy: All targets

Milestone n°6.012: Follow up on implementation framework for EU Biodiversity 2020 strategy

Work/Rationale: EU 2020 Biodiversity Strategy together with targets is a key instrument to enable the EU to reach its overall 2020 headline target "Halting the loss of biodiversity and the degradation of ecosystem services in the EU by 2020, and restoring them in so far as feasible, while stepping up the EU contribution to averting global biodiversity loss". Common Implementation Framework (CIF) for the EU Biodiversity Strategy to 2020 includes the governance aspects related to the coherent framework for monitoring, assessing and reporting on progress towards reaching the EU targets and streamlining this work as far as possible with monitoring, assessment and reporting obligations under the CBD (notably the Aichi Targets).

Output: Make use of Common Implementation Framework (CIF) as the framework for monitoring, assessing and reporting on progress towards reaching the biodiversity related PA 6 targets

Responsible: Danube Region MS and HR

Deadline: ongoing (following adoption of the Common Implementation Framework)

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020

- Relation to EU Biodiversity 2020 Strategy: All targets

- ICPDR Involvement: Achievement of good status of waters will improve the living conditions for key water dependent species

Milestone n°6.013: Assessment made for Danube Region on progress achieved towards Strategic Plan for Biodiversity 2011-2020 and Aichi Biodiversity Targets

Work/Rationale: In decision X/10, CBD COP 10 decided that the fifth national reports, due by 31 March 2014, should focus on the implementation of the 2011-2020 Strategic Plan and progress achieved towards the Aichi Biodiversity Targets. According to countries 5th national reports to the CBD analysis will be compiled for Danube Region on implementation of the 2011-2020 Strategic Plan and progress achieved towards the Aichi Biodiversity Targets.

Output: Updated information/compiled analyses on progress for implementation of the 2011-2020 Strategic Plan

Countries involved: Danube Region Countries

Deadline: Assessment prepared in I quarter 2015

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020

- Relation to EU Biodiversity 2020 Strategy: All targets

Action 2: “To manage Natura 2000 sites and other protected areas effectively”- Natura 2000”.

Action 6.2 “To manage Natura 2000 sites and other protected areas effectively”

Natura 2000 sites designated under the Birds and Habitats directives, as well as other protected sites should in principle have their own management plans or some other kind of contractual framework. But in practice, they often work in isolation and not efficiently enough. The effective management helped by transnational cooperation (networking) is necessary. The action should include exchange of experience and capacity building for protected areas/Natura 2000 sites administrations; community involvement; visitor management and tourism development; coordinated management planning, implementation and evaluation. It is also indispensable to increase public awareness about Natura 2000 sites and protected areas, with the help of e.g. the National Ecological and Rural Networks or the European Network for Rural Development. The action could be implemented e.g. through the existing Danube Network of Protected Areas and the Carpathian Networks of Protected Areas. ALPARC can serve as successful examples.

Milestone n°6.021: Follow up on reports prepared by EC for management of N2000 in Danube Region on implementation of conservation measures

Work/Rationale: For Natura 2000 sites MS shall establish the necessary conservation measures involving, if need be, appropriate management plans specifically designed for the sites or integrated into other development plans, and appropriate statutory, administrative or contractual measures which correspond to the ecological requirements of the natural habitat types in Annex I and the species in Annex II present on the sites.

Output: Overview on status of conservation measures implementation for N2000

Countries involved: Danube Region MS Countries

Deadline: following reports preparation by COM

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020

- Relation to EU Biodiversity 2020 Strategy: Target 1, Action 1 Complete the establishment of the Natura 2000 network and ensure good management

- Relation to other EUSDR PA targets&actions:PA4 Action - “To implement fully the Danube River Basin Management Plan (DRBMP)”

- ICPDR Involvement: ICPDR DRBMP is potentially a key element of a transnational spatial planning and development policy also contributing to Action 9 (To prepare and implement transnational spatial planning and development policies for functional geographical areas) of PA 6

Milestone n°6.022: Build capacity among riverine countries in Danube region

Work/Rationale: Coordination, cooperation and consultation among riverine countries strengthen links and build capacity for effective management of N2000 and PA

Output: Capacity built for development of management framework

Countries involved: Danube Region Countries

Deadline: to be set out on national level

- Relation to other EUSDR PA6 targets&actions: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020

- Relation to EU Biodiversity 2020 Strategy: Target 1, Action 1 Complete the establishment of the Natura 2000 network and ensure good management

- Relation to other EUSDR PA targets&actions:

Milestone n°6.023: Assessment made for Danube Region according to assessment of conservation status and effectiveness of measures (management framework of Natura 2000 sites) for period 2007-2012 due to in 2013 prepared by the MS/COM

Work/Rationale: Article 17 requires Member States to report every six years about the progress made with the implementation of the Habitats Directive. As the main focus of the directive is on maintaining and/or restoring a favourable conservation status for habitat types & species of community interest, monitoring & reporting under the directive is focusing on that. MS/EC have obligation to prepare assessment of conservation status and effectiveness of measures for period 2007-2012 due to in 2013.

Output: Assessment of conservation status and effectiveness of measures (management framework of Natura 2000 sites) for period 2007-2012

Countries involved: Danube Region EU Countries

Deadline: 2014 (following submission of reports of MS and preparation of composite report by COM)

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020

- Relation to EU Biodiversity 2020 Strategy: Target 1, Action 1 Complete the establishment of the Natura 2000 network and ensure good management and Action 4: Improve and streamline monitoring and reporting

Milestone n°6.024: Follow up on financial instruments available for financing N2000 network in next programing period 2014 - 2020 to assess adequate financing of Natura 2000 activities in EUSDR region

Work/Rationale: Different EU instruments (Rural Development funds, Cohesion and Structural Funds, IPA etc.) are available for financing Natura 2000 sites, with focus on long-term conservation benefits. In order to create funding opportunities to support PA6-related projects in the next programming period, Member States in the preparation of the Partnership Agreement and the Operational Programmes should take the EUSDR targets for preservation of biodiversity, landscapes and the quality of air and soils into account. Priority settings should be addressed in these documents.

Output: Compile information on the existing financing instruments in the next programming period (2014 – 2020)

Countries involved: Danube Region MS Countries

Deadline:  2014

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020

- Relation to EU Biodiversity 2020 Strategy: Target 1, Action 2 Ensure adequate financing of Natura 2000 sites

Milestone n°6.025: To establish Mura Drava Danube bilateral  Biosphere Reserve Hungary-Croatia

Work/Rationale: Hungary and Croatia jointly nominated Mura – Drava - Danube as the transbounary  biosphere reserve

- Milestones achieved: HU and HR signed Joint Declaration in September 2011; HU (in 2009) and HR (in September 2011) send the nomination for Mura  Drava – Danube Transboundary Biosphere Reserve to UNESCO MaB Program Secretariat; HR proclaimed Mura Drava Regional Park in February 2011

Output expected: Mura Drava Danube transboundary biosphere reserve proclaimed

Countries involved: Croatia and Hungary

Responsible contact point: Croatian – Hungarian Nature Conservation Sub-committee and Coordination Committee

Deadline: 2012

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020

- Relation to EU Biodiversity 2020 Strategy: Target 1, Action 1  Complete the establishment of the Natura 2000 network and ensure good Management

Milestone n°6.026: To establish Mura-Drava-Danube MAB Reserve Austria, Slovenia, Croatia, Hungary, and Serbia

Work/Rationale: Once established, this could be Europe’s largest trans-boundary riverine protected wetland area, and a strong candidate for UNESCO-recognized site including five riverine countries (AT, Sl, HR, HU and SRB).

- Milestones achieved: In March 2011 five countries signed joint Ministerial declaration and in October 2011 1st Meeting of the Coordination Board and International Working Group took place in HU, and 2nd meeting of Coordination Board and International Working Group took place in HR (12- 13 June 2012)

New identified project: WWF Project Protecting “Europe’s Lifeline” - The creation of a Trans-Boundary UNESCO Biosphere Reserve along the Danube, Drava and Mura Rivers (TBR MDD)

Output: Mura Drava Danube biosphere reserve proclaimed

Next steps: preparation activities for nomination for AT, SI and SRB (following the HU and RH example)

Countries involved: AT, HR, HU, SRB and SI

Responsible contact point: Members of the Coordination Board for the preparation of MDD TBR

Deadline: *following conclusions of the 2nd meeting of the Coordination  Board

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020

- Relation to EU Biodiversity 2020 Strategy Target 1, Action 1  Complete the establishment of the Natura 2000 network and ensure good management and Action 4: Improve and streamline monitoring and reporting

Milestone n° 6.027: DANUBEPARKS II - Anchoring the Danube River Network of Protected Areas as driver for transnational nature conservation strategies at the Danube

Work/Rationale: Interreg IVB Project, with the focus on networking and cooperation processes of protected areas alongside the Danube river. Project aims to further anchor the network on international and political level, content-oriented activities focus on flagship species (Black Poplar, White-tailed Eagle), River Morphology (cooperation with the ICPDR) and Tourism.

- Milestones achieved: Letter of Recommendation issued by PA6. Application submitted to Interreg IVB South East Europe Programme on 25.11.2011. Programme decision in June 2012

Output:  Wide public/stakeholder recognition for DANUBEPARKS network by long term use of the results by target groups on international, regional and local level throughout the Danube Region. Starting point for further Stakeholder involvement in PA6.

Countries involved: DE, AT, SK, HU, HR, RS, BG, RO

Responsible contact point: PAC 6 (BY), Florian Ballnus

Deadline: to be added after project approval (June 2012)

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2021

- Relation to EU Biodiversity 2020 Strategy: Target 1, Action 1  Complete the establishment of the Natura 2000 network and ensure good Management

- Relation to other EUSDR PA targets&actions: PA 6.03; PA 6.01; PA 6.13; PA 4.03; PA 4.01; PA 4.12; PA 5.02

Action 3: To protect and restore most valuable ecosystems and endangered animal species

Action 6.3 To protect and restore most valuable ecosystems and endangered animal species Enhanced protection of the remaining natural ecosystems, such as the Danube Delta or the Carpathians, wetlands restoration, afforestation of non-arable land, protection of marginal forests, bioremediation of highly impacted areas, supported by environmental research, are desirable. This is also crucial for endangered animal species protection, such as the Danube sturgeon62, brown bears, wolves, lynx and wild horses living in the Danube Delta. Research, inventory, and monitoring of species and habitats of European and national importance is an important part of this action. Conflicts with humans and illegal trade in wild animals should also be addressed.

Milestone n°6.031: Follow up on assessment made by MS and COM applicable for Danube Region to improve knowledge of ecosystems and their services in the EU

Work/Rationale: MS with the assistance of the COM will map and assess the state of ecosystems and their services in their national territory by 2014, assess the economic value of such services, and promote the integration of these values into accounting and reporting systems at EU and national level by 2020.

- Milestones achieved: On 28 April 2012, tender Mapping of ecosystems and their services in the EU and its Member States was published. The aim of this contract is to provide assistance on behalf of and in cooperation with the Commission to the Member States in the context of action 5 of the EU 2020 biodiversity strategy, on the mapping and assessment of the state of ecosystems and their services in their national territory, making best use of studies and work already undertaken at EU and Member State levels.

Output: Assessment prepared following EU mapping and assessing the state of ecosystems and their services

Countries involved: EUSDR EU MS

Deadline: 2014 (following preparation of the MS and COM assessment)

- Relation to EUSDR PA6 targets: By 2020, ecosystems and their services are maintained and enhanced by establishing green infrastructure and restoring at least 15% of degraded ecosystems, including degraded soils.

- Relation to EU Biodiversity 2020 Strategy: Target 2; Action 5 Improve knowledge of ecosystems and their services in the EU

- ICPDR Involvement: The ICPDR has performed economic analysis for the water use and water services. The total economic value of water should also cover the resource and environmental costs. Future activities include the assessment of economic benefits for environmental services, such as wetland conservation and the benefits of reducing nutrients, afforestation and reduction of erosion effects.

Milestone n° 6.032: Follow up on assessment made by MS and COM on strategic framework to set priorities for ecosystem restoration to identify priority restoration project for EUSDR region

Work/Rationale: MS with the assistance of EC have to develop strategic framework to set priorities for ecosystem restoration at sub-national, national and EU level by 2014

Output: Assessment prepared following EU mapping and assessing the state of ecosystems and their services

Countries involved Danube Region Countries

Responsible contact point:

Deadline: December 2012 (project timeline: January 2011-December 2012)

New identified project: WWF Project “Wetland restoration in the Mura-Drava-Danube area” (January 2011-December 2012)

- Relation to EUSDR PA6 targets:

- To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020

- Secure viable populations of Danube sturgeon species and other indigenous fish species by 2020.

- By 2020, ecosystems and their services are maintained and enhanced by establishing green infrastructure and restoring at least 15% of degraded ecosystems, including degraded soils.

- Relation to EU Biodiversity 2020 Strategy: Target 2; Action 6 Set priorities to restore and promote the use of green infrastructure

- Relation to other EUSDR PA targets&actions: PA4: Action to reduce existing water continuity for fish migration in the Danube basin

Milestone n°6.033: Sub-Strategy on Sturgeon Conservation

Work/Rationale: Based on initiatives of WWF, IAD and other NGOs and networks, a long-term strategy on the conservation of Sturgeon Species in the Danube shall be developed

- Milestones achieved: 1st Meeting on 20.01.2012 in Vienna. Second meeting scheduled for August 2012 in Tulcea.

Output: Preparation of project applications for next funding period, channelling importance of topic in policy level.

Countries involved: Danube Region Countries

Deadline: 2020 (Secure viable populations of Danube sturgeon species and other indigenous fish species by 2020), mid-term deadlines to be fixed during next DSTF meeting.

- Relation to EUSDR PA6 targets: PA6 Target: Secure viable populations of Danube sturgeon species and other indigenous fish species by 2020.

- Relation to EU Biodiversity 2020 Strategy: Target 2: Maintain and restore Ecosystems and their services.

- Relation to other EUSDR PA targets&actions: PA4 : Action to reduce existing water continuity for fish migration in the Danube basin

Milestone n°6.034: Reproduction of populations of rare and endangered fish species – a necessary condition for biodiversity conservation and sustainable development of the Ukrainian-Slovak transborder area of the Tisa river basin. Short title: “Fish: joint basin – joint solutions”

Work/Rationale: Project focuses on four endangered fish species in the Tisa River Basin. It directly contributes to biodiversity conservation and sustainable development by reproducing rare and endangered fish species by jointly developing and implementing innovative methodologies and tools to restore natural populations of valuable fish species. An international fish reproduction centre of rare and endangered fish species shall be established.

- Milestones achieved: Letter of Recommendation issued by PA6. Application submitted to ENPI Hungary-Slovakia-Romania-Ukraine program in March 2012. Expected programme decision in December 2012.

Output:  1. Jointly developed, implemented methodologies and tools to restore natural populations of valuable fish species 2.International fish reproduction center “Regeneration” established 3.Rivers of Ukraine and Slovakia revitalized with 600.000 fry of rare and endangered fish species 4. Youth of the transborder region is action ready for biodiversity conservation on the local level

Countries involved: Ukraine, Slovakia

Responsible contact point: Radmila Ustych, FORZA, Agency for sustainable development of the Carpathian region, Mynajska str.27/39 88018 Uzhgorod Ukraine, www.forza.org.ua

Deadline: project approval in December 2012(following approval project timeframe will be added )

- Relation to EUSDR PA6 targets: Secure viable populations of Danube sturgeon species and other indigenous fish species by 2020.

- Relation to EU Biodiversity 2020 Strategy: Target 2: Maintain and restore Ecosystems and their services.

- Relation to other EUSDR PA targets&actions PA4 : Action to reduce existing water continuity for fish migration in the Danube basin

Action 4: To explore together the appropriateness of reviewing the Convention Concerning Fishing in the Waters of the Danube

Action 6.4 To explore together the appropriateness of reviewing the Convention Concerning Fishing in the Waters of the Danube

A Convention on fishing in the waters of the Danube river was signed in 1958 and has been in force since then. However neither recent geopolitical changes in the area nor policy developments related to the protection of the environment or to sustainable fishing have been reflected in the Convention. The parties to the Convention should examine this.

Milestone n°6.041: Built cooperation, if appropriate, among parties regarding review of the Convention

Work/Rationale: Explore possibilities of using the Convention Concerning Fishing in the Waters of the Danube as the EUSDR level

Output: to be added by the Danube Region Countries Parties to the Convention

Countries involved: Parties to the Convention Concerning Fishing in the Waters of the Danube

Deadline: to be added by the Danube Region Countries Parties to the Convention

- Relation to EUSDR PA6 targets: Secure viable populations of Danube sturgeon species and other indigenous fish species by 2020

- Relation to other EUSDR PA targets&actions - PA4 : Action to reduce existing water continuity for fish migration in the Danube basin

Action 5: To develop green infrastructure in order to connect different bio-geographic regions and habitats

Action 6.5 To develop green infrastructure in order to connect different bio-geographic regions and habitats

The habitats (including Natura 2000 sites) can better keep and enhance their value, if they are interconnected and this is the way to ensure that ecosystem services are being kept provided. The action could include scientific research to find new ways for connecting habitats, consultations with relevant communities and stakeholders, careful and integrated spatial planning to develop and apply practices and technologies for economic investments and infrastructural development benefiting biodiversity. Construction of e.g. ecobridges, eco-ducts and ecological "stepping stones" should be part of a planning of infrastructure building.

Milestone n°6.051: Assessment made to identify activities to be implemented in Danube Region countries form EU Green Infrastructure Strategy to best fit the EUSDR targets

Work/Rationale: After adoption of the EU Green Infrastructure Strategy (by 2012) identify activities to be implemented in EUSDR countries. The COM will develop a Green infrastructure Strategy by 2012 to promote the deployment of green infrastructure in the EU in urban and rural areas, including through incentives to encourage up-front investments in green infrastructure projects and the maintenance of ecosystem services, for example through better targeted use of EU funding streams and Public Private Partnerships.

Output: Assessment prepared following EU mapping and assessing the state of ecosystems and their services

Countries involved: Danube Region Countries

Deadline: 2013 following development of Green Infrastructure Strategy

- Relation to EUSDR PA6 targets: By 2020, ecosystems and their services are maintained and enhanced by establishing green infrastructure and restoring at least 15% of degraded ecosystems, including degraded soils.

- Relation to EU Biodiversity 2020 Strategy: Target 2; Action 6 Set priorities to restore and promote the use of green infrastructure

Milestone n°6.052: Follow up on implementation of green corridors projects identified in EUDSR Action Plan

Work/Rationale: EUSDR action plan identified 2 green corridors Lower Danube (RO, BL, MO, UA) and Alpine-Carpathian Corridor (AT, SK)

Output: Priority actions identified based on results of green corridors projects and its possible financing mechanisms (new project generation)

Countries involved: RO, BL, MO, UA (Lower Danube) and AT, SK (Alpine-Carpathian Corridor)

Deadline: to be set out by countries involved

- Relation to EUSDR PA6 targets: By 2020, ecosystems and their services are maintained and enhanced by establishing green infrastructure and restoring at least 15% of degraded ecosystems, including degraded soils.

- Relation to EU Biodiversity 2020 Strategy: Target 2; Action 6 Set priorities to restore and promote the use of green infrastructure

- ICPDR Involvement: The outlined projects contribute to the goals of the Danube River Basin Management Plan

Action 6: To reduce the spread of invasive alien species (IAS)

Action 6.6 To reduce the spread of invasive alien species (IAS)

The action would assess the impact of IAS on the ecosystems in the Danube region, identify environmentally friendly ways to control their development, promote research to identify ecologically sound ways to keep their population under control or eliminate them and raise public awareness about the danger of IAS.

Milestone n°6.061: To assess the effectiveness of IAS legislation in EUSDR region analysing implementation on new legislative framework on IAS in EUSDR region

Work/Rationale: Legislative instrument to fill policy gaps in combating IAS to be developed by COM by 2012. Following the adoption of the new legislative framework on IAS proposal is to assess the effectiveness of IAS legislation in EUSDR region by analysing implementation on new legislative framework on IAS on national level.

Output: Assessment of effectiveness of implementation on new legislative framework on IAS on national level

Countries involved: Danube Region EU Countries

Deadline: 2013-ongoing, following adoption of  new legislative framework on IAS

- Relation to EUSDR PA6 targets: By 2020, Invasive Alien Species and their pathways are identified and prioritised, priority species are controlled or eradicated, and pathways are managed to prevent the introduction and establishment of new Invasive Alien Species

- Relation to EU Biodiversity 2020 Strategy: Target 5; Action 16 Establish a dedicated instrument on Invasive Alien Species

- ICPDR Involvement: Specific action under the Monitoring and Assessment (Water Quality) Expert Group (MA EG) related to invasive aquatic species

Action 7: To decrease the input of pesticides into the environment of the Danube Region

Action 6.7 To decrease the input of pesticides into the environment of the Danube Region

To reduce the contamination of the Danube Region with pesticides, the countries of the Danube Region should use efficiently the possibilities of the Pesticide Framework Directive (PFD) establishing a framework for Community action to achieve the sustainable use of pesticides. PFD outlines aims and effective ways to reduce both the total amount of used pesticides and the toxicity of pesticides. The action should especially be focused on the development of ambitious programs and concepts for a reduction of pesticides in general or in specific areas as well as on the initiation of hot spot management or restrictions for the application of pesticides, e.g. by establishing buffer strips or compensating areas.

Milestone n°6.071: work will be defined in the next reporting period

Work/Rationale:

Milestones:

Output:

Countries involved:

Responsible contact point:

Deadline:

- Relation to EUSDR PA6 targets

- Relation to other EUSDR PA targets&actions

- ICPDR Involvement: Pressures and Measures Expert Group has been evaluating and reporting on issues related to input of pesticides into the environment of the Danube Region (no specific project or direct action has been taken); Activities are organized to assess the implementation status and effects of the agri-environmental measures, as part of the Common Agricultural Policy/Rural Development Policy supporting the WFD objectives.

Action 8: To remove safely obsolete pesticides and other obsolete chemicals in the area of Danube Region

Action 6.8 To remove safely obsolete pesticides and other obsolete chemicals in the area of Danube Region and implementing the World Health Organisation (WHO)’s Resolution on Improvement of health through sound management of obsolete pesticides and other obsolete chemicals, adopted at the 63rd World Health Assembly (WHA) which took place in May 2010 in Geneva.

Milestone n°6.081: work will be defined in the next reporting period

Work/Rationale:

Milestones:

Output:

Countries involved:

Responsible contact point:

Deadline:

- Relation to EUSDR PA6 targets:

- Relation to other EUSDR PA targets&actions:

- ICPDR Involvement: The Accident Risk Site Inventory includes some sites which contain obsolete chemicals

Action 9: To prepare and implement transnational spatial planning and development policies for functional geographical areas (river basins, mountain ranges etc.)

Action 6.9 To prepare and implement transnational spatial planning and development policies for functional geographical areas (river basins, mountain ranges etc.)

The conservation of ecosystems and natural assets, along with the assertion of a sustainable growth perspective contribute to the enhancement of the quality of life and employment opportunities for local population. The aim is the development of coordinated spatial planning policies focusing on the protection and at the same time sustainable development of the functional geographical areas,

based on its strengths and potential.

Milestone n°6.091: BIOREGIO Carpathians - Integrated management of biological and landscape diversity for sustainable regional development and ecological connectivity in the Carpathians

Work/Rationale: Project co-funded under the European Transnational Cooperation South East Europe Programme - The BIOREGIO Carpathians is aimed at enhancing the integrated management of the Carpathians protected areas and natural assets in a transnational context and thereby increase the attractiveness of the region.

Output: Implementation of the Carpathian Convention Biodiversity Protocol, Development of a Carpathian Joint Biodiversity Information System and of a Red List of Species and Habitats, Fostering of ecological connectivity and promotion of the integrated management of protected areas.

Countries involved:  AT, HU, IT, RO, SK, CZ, PL, SRB, UA

Responsible contact point: NFA (National Forest Administration) ROMSILVA - Piatra Craiului National Park Administration, Romania. Contact person: Mircea Verghelet, Park Director.

Deadline: December 2013 (project timeline: 01 January .2011- 31 December 2013)

- Relation to EUSDR PA6 targets To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2021

- Relation to EU Biodiversity 2020 Strategy Target 1, Action 1  Complete the establishment of the Natura 2000 network and ensure good management

- Relation to other EUSDR PA targets&actions PA 6.01; PA 6.02; PA 6.03; PA 6.05; PA 6.06

Milestone n°6.092: Carpathian Convention Working Group on Spatial Development

Work/Rationale: Decision COP3/2, Terms of Reference for the Carpathian Convention Working Group on Spatial Development

Output: Support in development of projects implementing the Carpathian Convention and the Strategic Action Plan for the Carpathian Area, including projects implementing the EUSDR PA 6.09. Elaboration of a database of projects developed in the Carpathian Area, including projects implementing EUSDR PA 6.09.

Countries involved: Carpathian Convention Countries (CZ, HU, PL, RO, SRB, SL and UA)

Responsible contact point:

Deadline: Mid 2014

- Relation to EUSDR PA6 targets: By 2020, ecosystems and their services are maintained and enhanced by establishing green infrastructure and restoring at least 15% of degraded ecosystems, including degraded soils

Relation to EU Biodiversity 2020 Strategy: All targets of the Strategy

Action 10: To ensure appropriate treatment of solid waste

Action 6.10 To ensure appropriate treatment of solid waste

Integrated waste management systems should be established and implemented on national, regional and local level. The development of waste management centres for municipal and non-hazardous waste is needed, as well as rehabilitation and closure of incompliant landfills and highly polluted and contaminated sites and wild dumps. The action should also include awareness-raising about the needs of reducing and recycling waste.

Milestone n°6.101: SMIWASTRES (“Transfrontier collaboration for establishment of efficient System for Municipal and Industrial Waste Treatment on the basis of their Sorting”)

Work/Rationale: Project focuses on measures to minimise industrial, municipality and rural waste which in turn shall improve environmental, economic and social issues in EUSDR area.  Single activities encompass the elaboration of a common platform for current and future waste treatment systems, joint development of a Waste Collection-Sorting-Processing-Disposal cycle, guidelines and recommendations for policy level. The objectives of the project foresee a practice-based best practice examples for the entire waste treatment cycle and their dissemination, qualification measures for staff, joint legal framework.

Milestones: Letter of Recommendation issued by PA6. Application submitted to ENPI Joint Operational Program "Romania-Ukraine-Republic of Moldova" 2007-2014.

Output:  Waste separated collection, processing, utilisation & disposal; EUSDR/EaP agreed Legal-Normative promotion PPP for IPPC & BAT; Productive & informational-methodical basis for complete Waste Treatment System; Monitoring & Staff Skills facilitation on basis of modern Information-Expert Institutions through PPP principles & interactive Web-site

Countries involved: RO, UA, MD

Responsible contact point: Mr. Georiy Leontiy, Director of Department of Housing & Communal Service of Chernivtsi Regional State Administration, Ukraine, Dr. Zinoviy S.BROYDE, Director of Centre "EcoResource", UKRAINE

Deadline: Project Approval in 2012 (project timeframe will be added flowing projects approval). Update (June 2012): the project has not been approved by the ENPI Joint Operational Program.

- Relation to EUSDR PA6 targets: By 2020, ecosystems and their services are maintained and enhanced by establishing green infrastructure and restoring at least 15% of degraded ecosystems, including degraded soils.

- Relation to other EUSDR PA targets&actions: PA 4 (treatment of hazardous substances and contaminated sludge with the newest and best available technology); PA 6.15; PA 8

Milestone n°6.102: To develop Solid waste management strategies

Work/Rationale: Pursue the work on waste management particular as regards construction of the waste management centres and remediation of the existing landfills and hot-spots.

Output: Solid waste management strategies developed

Countries involved: Danube Region EU Countries

Deadline: to be set out on national level

- Relation to EUSDR PA6 targets: By 2020, ecosystems and their services are maintained and enhanced by establishing green infrastructure and restoring at least 15% of degraded ecosystems, including degraded soils

- Milestone n°6.103: Identify, agree on, design and implement the projects at the Upper Tisza Region floodplains

Work/Rationale: The contamination of floodplains is waste management but also nature and landscape protection issue. This situation at the Upper Tisza Region floodplains claims a large scale of international cooperation. Therefore, potential projects in the field of “Elimination of waste and improvement of local waste management at the flood area of Upper Tisza Region” through cross-border coordination - involving competent governmental authorities, NGOs, potential stakeholders and partners have to be identified.

Output: list of potential projects e.g. Cross border capacity building and awareness raising for waste elimination in the at the flood area of the Upper Tisza Region aiming at better local waste management and Cross-border infrastructural development for waste elimination at the flood area of the Upper Tisza Region

Countries involved: Danube region countries in Upper Tisza Region (Slovakia, Romania and Ukraine)

- Relation to EUSDR PA6 targets: By 2020, ecosystems and their services are maintained and enhanced by establishing green infrastructure and restoring at least 15% of degraded ecosystems, including degraded soils

Action 11: To create standardised and compatible information on land cover on transnational basis

Action 6.11 To create standardised and compatible information on land cover on transnational basis

Within the Global Monitoring for Environment and Security (GMES) framework, one of the main services that will be available is a land monitoring service. However, rather limited information on land resources is available for the Danube Region. Actions should thus focus on the possibilities to collect harmonised land cover information from national sources and to create standardized and compatible information on land cover on transnational basis.

Milestone n°6.111: To collect harmonised land cover information

Work/Rationale: work will be defined in the next reporting period

Milestones:

Output:

Countries involved:

Responsible contact point:

Deadline:

- Relation to EUSDR PA6 targets

- Relation to EU Biodiversity 2020 Strategy

- Relation to other EUSDR PA targets&actions

- ICPDR Involvement: The Danube GIS has evaluated some elements of this issue. For calculation of harmonized inventory of point and diffuse sources of pollution, for pressures assessment and scenarios calculations, information on land cover have been collected and assessed. Input data (also information for calculating erosion, run off, land use, etc) are updated and new scenarios calculations are expected to be available for assessing the effect of agricultural measures implemented in the Danube Region Basin.

Action 12: To raise awareness about soil protection

Action 6.12 To raise awareness about soil protection

This action could be achieved in cooperation with the European Land and Soil Alliance (ELSA), including more than 100 members from 7 Member States. Further partnerships in the Danube Region should be initiated on communal level and in the educational domains.

Milestone n° 6.121: SONDAR - Soil Strategy Network in the Danube Region

Work/Rationale: Project. SONDAR is aimed at achieving quantitative and qualitative soil protection through awareness raising. Demonstrations will be carried out throughout the region and documented. Furthermore, specially-educated "soil ambassadors" will be trained and a coordination office for the European Land and Soil Alliance will be established. A direct link to PA6 / EUSDR has been established.

- Milestones achieved: International Conference 28 March 2012 (St. Pölten, AT) which marked the start of cooperation between PA6 / PAC and SONDAR project.

Output: To promote awareness raising activities in the field of soil protection and sustainable development in the Danube Region

Countries involved: AT, HU, SK, CZ

Responsible contact point: Project Responsible: Office of Lower Austrian Government, Dr. Erwin Szlezak, Department of Rural Development

Deadline: December 2013 (project duration 02/2011 - 12/2013 (HU - AT), 11/2010 - 10/2013 (SK - AT))

- Relation to EUSDR PA6 targets: By 2020, ecosystems and their services are maintained and enhanced by establishing green infrastructure and restoring at least 15% of degraded ecosystems, including degraded soils.

- Relation to other EUSDR PA targets actions: PA 6.15

- ICPDR Involvement: Joint Programme of Measures contains measures related to soil protection (currently monitored)

Action 13: To decrease air pollutants

Action 6.13 To decrease air pollutants

All Danube region countries have signed the Convention on long-range transboundary air pollution. In compliance with this Convention, there is a need to report about the level of air pollutants in the region. The action should concentrate on data collection and reduction measures.

Milestone n° 6.131: Upgrading and further development of the monitoring network on air pollutants

Work/Rationale: Danube region countries as signatures to Convention on long-range transboundary air pollution need to report about the level of air pollutants in the region (action should concentrate on data collection and reduction measures).

Output: work will be defined in the next reporting period

Countries involved: Danube Region Countries

Deadline:

- Relation to EUSDR PA6 targets To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020

- Relation to other EUSDR PA targets&actions

Milestone n° 6.132: To take measures to gradually reduce the pollution, along the limit values for certain pollutants

Work/Rationale: work will be defined in the next reporting period

Output:

Countries involved: Danube Region Countries

Deadline:

- Relation to EUSDR PA6 targets

- Relation to other EUSDR PA targets&actions

Action 14: To raise awareness of the general public, by acknowledging and promoting the potentials of natural assets as drivers of sustainable regional development

Action 6.14 To raise awareness of the general public, by acknowledging and promoting the potentials of natural assets as drivers of sustainable regional development

It would increase the perception of preserved nature as a valuable asset. Promotion of green, soft and eco-tourism is envisaged as a part of this action.

Milestone n° 6.141: Keep updated INTERACT portal on EUSDR regarding best available information on PA6 activities, projects and financing mechanism

Work/Rationale: INTERACT established web page www.danube-region.eu on promotion of EUSDR. SG members are urged to use Interact web page for communication and exchange of information and encouraged all members to join the Priority Area 06 Group.

Output: Regular maintenance and update of www.danube-region.eu web page for PA 6

Countries involved: Danube Region Countries

Responsible contact point: PA 6 PACs

Deadline: on-going

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020.

- Relation to EU Biodiversity 2020 Strategy: Target 1. Action 3 Increase stakeholder awareness and involvement and improve enforcement

Milestone n° 6.142: Implement stakeholder awareness communication activities for Natura 2000 in EUSDR region parallel with COM/MS communication campaign on Natura 2000

Work/Rationale: The COM, together with MC will develop and launch a major communication campaign on Natura 2000 by 2013. To increase stakeholder awareness and involvement Danube Region MS will follow on the activities and outlines proposed by the strategy.

Output: Stakeholder awareness communication activities implemented

Countries involved: Danube Region MS Countries

Deadline: ongoing, following the launch of the communication campaign on Natura 2000

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020”.

- Relation to EU Biodiversity 2020 Strategy: Target 1. Action 3: Increase stakeholder awareness and involvement and improve enforcement

- Relation to other EUSDR PA targets&actions:  PA5 Action - “To strengthen general awareness and facilitate exchange of good practice in integrated water management issues in the Danube Basin among decision-makers at all levels and among the population of the Region”

Milestone n°6.143: Organisation of stakeholders seminars and workshops and conferences

Work/Rationale: To enhance visibility of the EUSDR specific and demand-driven workshops, seminars and conferences in order to expand the stakeholder`s network and to develop new projects will be organised.

Output: Stakeholders seminars and workshops and conferences organised

Countries involved: Danube Region Countries

Deadline: ongoing (To demonstrate the horizontal exchange within Pillar II, a joint Stakeholder Workshop is envisaged to take place in September in Budapest.)

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020.

- Relation to EU Biodiversity 2020 Strategy: Target 1. Action 3: Increase stakeholder awareness and involvement and improve enforcement

Milestone n°6.144: Implementation of Green Danube Network project

Work/Rationale: Project to network environmental NGOs in the Danube Region to promote biodiversity, natural protection and to raise awareness, in context with EUSDR.

Output: Green Danube Network project implemented (*please note project application to EU COM  (EAC-EA Europe for Citizens))

Countries involved: DE (BY), AT, HU

Responsible contact point: PAC 6 (BY), Florian Ballnus

Deadline: Project approval in 2012

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020”.

- Relation to EU Biodiversity 2020 Strategy: Target 1. Action 3: Increase stakeholder awareness and involvement and improve enforcement

Milestone n° 6.145: Follow up on the visibility activities across all identified EUSDR PA6 projects

Work/Rationale: Taking into account that all the projects, especially biodiversity related ones have visibility activities it is proposed that project leaders together with the national contact points for PA6 and PAC will gather information on the visibility activities taking place Danube Region and find the most appropriate means to disseminate information further.

Output: Visibility activities deriving from the Danube Region PA 6 projects disseminated Countries involved: Danube Region Countries

Responsible contact point:  Project leaders of PA 6 identified projects and PACs and NCPs

Deadline:  ongoing, following the implementation of PA 6 identified projects

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2021

- Relation to EU Biodiversity 2020 Strategy: Target 1. Action 3: Increase stakeholder awareness and involvement and improve enforcement

- ICPDR Involvement: Evaluating possibilities to inter-link existing educational initiatives and youth programs; the Danube Box (comprehensive educational tool) part of “Connecting People to the Danube” project

Action 15: To educate children and young people

Action 6.15 To educate children and young people

Since there is a growing pressure on biodiversity and natural resources become scarcer, there is a particular need to educate the young generation. This should cover the services provided by ecosystems, value of natural assets and benefits for conservation of biodiversity. Part of the action could be devoted to the introduction of environmental education into the educational curricula of the Danube countries.

Milestone n° 6.151: In line communication activities from communication campaign on Natura 2000 further develop and promote activities including children and young people

Work/Rationale: The COM with MS will develop and launch a major communication campaign on Natura 2000 by 2013. To increase stakeholder awareness and involvement especially in regards to education of children and young people Danube Region MS will follow on the activities and outlines proposed by the strategy.

Output: Communication activities related to Natura 2000 further developed and promote activates including children and young people

Countries involved: Danube Region Countries

Deadline:  on going, following the launch of the communication campaign on Natura 2000

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2021

- Relation to EU Biodiversity 2020 Strategy: Target 1. Action 3: Increase stakeholder awareness and involvement and improve enforcement

- ICPDR Involvement: The Danube Box (comprehensive educational tool) part of “Connecting People to the Danube” project

Action 16: To build capacities of local authorities in the environment-related matters

Action 6.16 To build capacities of local authorities in the environment-related matters

Local authorities are primarily responsible for the implementation of environment related matters, such as waste or protected areas management. Often, they lack knowledge and capacities to develop projects in the environmental area. Under this action, the local authorities would be provided with training, an expert group helping regions and cities resolving problems would be established, and networks for exchange of good practices.

Milestone n°6.161: Implement guidance document to improve understanding of the key sector of EU nature legislation

Work/Rationale:  The COM and MS will improve cooperation with key sectors and continue to develop guidance documents to improve their understanding of the requirements of EU nature legislation and its value in promoting economic.

Output: Cooperation with key sectors improved using implement guidance document on EU nature legislation

Countries involved: Danube Region MS Countries

Deadline: on going, following the development of develop guidance documents on EU nature legislation and its value

- Relation to EUSDR PA6 targets: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2021

- Relation to EU Biodiversity 2020 Strategy: Target 1. Action 3: Increase stakeholder awareness and involvement and improve enforcement

X/2 Decision: The Strategic Plan for Biodiversity 2011-2020 and the Aichi Biodiversity Targets http://www.cbd.int/doc/decisions/cop-10/cop-10-dec-02-en.pdf

By COP11 relevant information from Parties on starting process for revised and updated national biodiversity strategies and action plans will be prepared. Based on information presented for consideration to the CBD CoP 11 indicative assessment on the progress related to the Milestone 6.011 will be prepared in 2013. This will be used as indicative information in period till assessment due in I Q 2015

COM(2011)244 final EU 2020 Biodiversity Strategy http://ec.europa.eu/environment/nature/biodiversity/comm2006/pdf/2020/1_EN_ACT_part1_v7%5b1%5d.pdf

http://www.naturstyrelsen.dk/NR/rdonlyres/1A3B958F-A6A8-4269-89FA-667378864EDF/141036/BackgroundPaperEUBiodivStrategyCIF.pdf

Decision X/10 National reporting: review of experience and proposals for the fifth national report http://www.cbd.int/doc/decisions/cop-10/cop-10-dec-10-en.pdf

http://wwf.panda.org/what_we_do/where_we_work/black_sea_basin/danube_carpathian/news/?199772/Worlds-first-five-country-protected-area-to-conserve-Europes-Amazon

http://www.ptice.hr/dokumenti/2011_FS%20MAVA_engl.pdf

As defined in Target 2; Action 5 in COM (2011) 244 final

http://awsassets.panda.org/downloads/letak_eng.pdf

As defined in Action 6b in COM (2011) 244 final

As defined in Action 16 in COM (2011) 244 final

"Directive 2000/60/EC of the European Parliament and of the Council establishing a framework for the Community action in the field of water policy" or, in short, the EU Water Framework Directive (WFD)

http://www.carpathianconvention.org/NR/rdonlyres/E7E0FE2C-BDA1-4E4D-B6F0-686DB8D15E37/0/FINALrevisedToRs_WGSpatialDevelopment.pdf

http://www.sondar.eu/sk/index.php?article_id=17&clang=2

To be used s communication tool for SG members and as the visibility tool for other stakeholders

As defined in Action 3a in COM (2011) 244 final

As defined in Action 3a in COM (2011) 244 final

Following on the Action 3b in COM (2011) 244 final