Report to the European Commission

Implementation of the EUSDR Priority Area 6 to preserve biodiversity, landscapes and the quality of air and soils

Reporting period

13 April 2011 – 30 June 2012

Final

# Overall progress

## State of play

### Work on the policies

In order to ensure efficient implementation of EUSDR, implementation of Priority Area 6 started right with the nomination of the Priority Area Coordinators in Bavaria and Croatia in February 2011. During the first half of the year, until the final endorsement of the EUSDR by the EU Council and the first Steering Group meeting in June 2011, work was mainly focussed on organisational settings at PAC level, but also on the high level political kick off conferences and meetings, in order to give a clear signal that the EUSDR and PA6 was starting its activities.

Danube Summit and political kick-off meeting of the responsible ministries of Pillar II (Environment) of the EUSDR on 26 May 2011 in Niederalteich (Bavaria) was endorsed by  Signing of Joint Declaration by the high level country representatives responsible for the coordination of the Pillar ‘Protecting the Environment in the Danube Region’ (PA4: HU & SK, PA5: HU & RO, PA6: DE & HR). With this event and the Joint Declaration a strong will for cooperation was expressed by a high level political commitment which marked the beginning of close cooperation of PACs and involved policy makers in the Environmental Pillar II.

7-8 June 2011, Ingolstadt (Bavaria): International Conference: “The EU Strategy for the Danube Region. The Danube Strategy within the Context of European Policy” was organized by Southeast Europe Association and Bavarian State Minister for Federal and European Affairs, Emilia Müller. In a workshop session, PA6 Coordinators presented for the first time their work plan and foreseen implementation activities, followed by an open discussion with main target groups of PA6.

The targets and actions of PA6 have been communicated to relevant departments of foremost ministries responsible for environmental issues in the involved countries and to the Steering Group members. It proved that it takes a considerable time to inform about the general aims and objectives, as well as on the organisational framework of the EUSDR on policy level, due to the complexity of the Strategy and the need to introduce new ways of decision making processes and respective ways of communication. PA6 Coordinators have high political support, regular meetings and exchange of information and follow up on the progress on national and regional level trough all pillars of the EUSDR.

An ongoing challenge for the PACs is to streamline and align the work done on project level with the policy level in order to make decision makers aware of the benefit of getting connected to the EUSDR.

Table 1: Follow up on the events in the reporting period

| DATE | VENUE |
| --- | --- |
| 16-17 February 2011 | Conference of the EU Strategy for the Baltic Sea Region in Gdansk, Poland, first meeting of PACs of EUSDR and EU COM. |
| 12 April 2011 | Working meeting of PA6 Coordinators with desk officer from DG Regional Policy in Brussels, clarification of role of PACs and discussion on next steps. |
| 8-10 May 2011 | First official conference of EUSDR with PACs, National Coordinators and EU COM in Gödöllö (HU) |
| 15 December 2011 | International Conference “Danube Strategy - An Impetus for Strengthening Regional Cooperation between Croatia, Hungary and Serbia” organized by Institute for International Relations (IMO), Zagreb and Friedrich Ebert Stiftung, Zagreb in Zagreb, Croatia |
| 20 December2011 | International Seminar “…about the Danube Region”, Vienna University of technology, by invitation of Vice chancellor a. D. Hon. Prof. Dr. Erhard Busek (Ad personam Jean Monnet Chair). Presentation by PAC (BY) on PA6, exchange with PA1a further established. |
| 26 January 2012 | DaNet Conference, Osijek, Croatia. The aim of the Conference was to provide NGOs from Hungary, Serbia, Croatia, Bosnia & Herzegovina, Slovenia with information about and better understanding of the Danube Strategy and to facilitate establishment of networks for the success of the Danube Strategy (DANUBENET). |
| 30-31 January 2012 | 2nd meeting of national contact points and Priority Area Coordinators in Bucharest with intense discussion on state of play in the implementation. |
| 24 April 2012 | Joint Research Centre Conference “Scientific Support to the Danube Strategy” (in Brussels), focus on Environment protection, irrigation and agricultural development, navigability, energy production and European governance. PAC6 (BY) noticed that it could further network with relevant universities and research institutions and highlighted the need for horizontal approach of EUSDR, which could be fostered by scientific community. |

1.1.2. Work on actions in regard to Roadmaps as deliverable

Summarizing the experiences made in the implementation of PA6 of the EUSDR it has to be stated that even though the political commitment concerning the EUSDR is given in general, specific implementation-oriented actions are highly depending on committed actors on the ground and on available funding schemes and programmes. A successful implementation of PA6 therefore calls primarily for a bottom-up driven process rather than a standardized top down approach to be performed by SG members or even the political level. This is not necessarily a disadvantage but has to be kept in mind in order to raise added value out of the EUSDR.

The coordinating work of the PACs in PA6 should therefore focus on supporting existing and emerging initiatives and projects in line with the set targets (as the example of the Danube Sturgeon Task Force). Furthermore, it became evident that the targets and actions from the Action plan are comprehensive and have a long-term perspective. Different approaches for definition of milestones, projects and initiatives can be taken in consideration for their achievement. It was identified that breaking down actions in milestones, deadlines and responsibilities by the PACs without having a real ownership for these elements on the side of committed actors and project holders will not prove to be successful. It is evident that ownership and commitment is needed by the project leaders who in the end do the implementation, mostly for projects which are in turn dependent on funding to get into action.

Considering this, the PACs have to align their efforts together with existing and emerging initiatives and projects and enhance their visibility not only but especially to the policy level by using the EUSDR momentum. Flexible means of operational implementation within the PA6, adapted according to the respective demands and opportunities, are considered as a key success factor in implementing the EUSDR.

## Process

1.2.1. Setting up the organisational structure

After nomination of PACs in February 2011, main focus until June 2011 was on organisational issue, such as setting up the structure (“organigram”) with all involved actors and highlighting the need for horizontal exchange among PACs. This first phase was successfully accompanied by two Lab Group meetings, in order to reach a common understanding about the role and the tasks of the PACs and other actors (e.g. NC, EU COM, Interact, Steering Group) from the beginning. The conference in Gödöllö also contributed to reach this aim.

Pillar II cooperation: Quite from the beginning, initiated by the High level Danube Summit (Joint declaration by the country representatives responsible for the coordination of the Pillar ‘Protecting the Environment in the Danube Region’) intense exchange among Pillar II PACs 4, 5 & 6 has been initialized and formalized, due to the thematic overlapping of targets and actions and the benefits of mutual support and cooperation. The Pillar II cooperation is also based on the Niederalteich summit as described above. On 17 November 2011 first working meeting of all Pillar II PACs took place at the premises of Interact in Vienna. The scope of cooperation was discussed and agreed; main results of the Pillar 2 cooperation are on operative level:

- Development of Flow chart “Labelling procedure” for Pillar II

- Joint development of “project data sheet”, in excel format, which serves as application form for projects which are currently developed and want to apply for Labelling and to receive a Letter of Recommendation of PA 4, 5 or 6

- Joint development of selection criteria for Labelling, approved by Steering Groups of PA 4, 5 and 6

- Joint development of Fact Sheet on Labelling process, describing the work flow on how to get labelled and receive Letter of Recommendation to applicants (to be published on the website after Steering Group approval).

- Harmonized wording of Letter of Recommendation (based on proposal by EU COM)

On the content side, exchange among the Pillar II PACs takes also place within discussion on projects, e.g. concerning overlapping and PACs’ main responsibilities. Furthermore, as defined by the Rules of procedures, each PAC of Pillar II is automatically observer in the other two PAs’ Steering Groups and therefore all PACs are mutually participating in Steering Group meetings.

In order to demonstrate the horizontal exchange within Pillar II, a joint Stakeholder Workshop is currently in preparation, and is envisaged to take place in September 2012 in Budapest.

Cooperation of PACs from Bavaria and Croatia: From the beginning, the cooperation between the two PACs from Bavaria and Croatia has been very fruitful, cooperative and constructive. During the working process it became obvious that the approach to the implementation of the PA6 was quite similar and that contacts, networks and expertises from both PACs complement each other. Joint PA6 presentations at specific occasions demonstrated strong cooperation also to the outside.

Since 22 December 2011 field of nature protection and biodiversity conservation in Croatia is no longer under the competence of Ministry of Culture as it was in the previous period, but under the competence of the Ministry of Environment and Nature Protection and due to the change in expert staff new PAC was nominated accordingly.

Table 2: Follow up on PAC meetings in the reporting period

| DATE | VENUE |
| --- | --- |
| 16-17 February 2011 | First PAC meeting during EUSBSR conference in Gdansk |
| 16.-17 March 2011 | PAC meeting during 1st Labgroup meeting in Vienna |
| 12 April 2011 | Meeting of DG Regio Desk Officer and both PA6 PACs |
| 08-11 May 2011 | PAC meeting during EUSDR conference in Gödöllö |
| 01-02 June 2011 | PAC6 working meeting in Zagreb |
| 07-08 June 2011 | PAC meeting and joint presentation during conference in Ingolstadt |
| 14-15 June 2011 | PAC meeting during 2nd Labgroup Meeting, Budapest |
| 29-31 January 2012 | PAC meeting during EUSDR conference in Bucharest |
| 22 May 2012 | PAC6 working meeting in Zagreb |

Exchange with other PACs. Apart from the close cooperation among the Pillar II PACs, PAC6 also intensified exchange with other PACs, as listed below, in order to strengthen the further common approach and to avoid a singled out sectoral implementation of single Priority Areas. In particular the contacts and the activities encompass the following:

PAC1a (Inland Waterways): exchange and bilateral meeting in order to discuss the issue of the potentially conflicting objectives of PA1a and PA6. This is also due to the fact that critical reflection on EUSDR took place from the outside, especially with focus on these two specific Priority Areas. PAC6 (BY) and PAC 1a consider EUSDR as an opportunity to start a dialogue among the involved stakeholders and as a chance to overcome deep conflicts from the past. Joint activities of PAC6 and PAC 1a are intended for 2013, such as cross-sectoral discussion forums and workshops.

PAC9 (To invest in people and skills): common understanding of joint approach in implementation of EUSDR and recognition of the joint challenge to reach and activate the broader public in the EUSDR implementation process. Joint activities are intended where possible and appropriate.

PAC2 (To encourage more sustainable energy): electronic exchange on one specific action of PA2, with the request of PAC2 to shift it to PA6 (Action “To reinforce the Carpathian Convention to share best practices on using biomass for energy purposes”). After discussion, it was agreed that the action remains with PA2, but PA6 will support related projects and can participate at related events, also to demonstrate the holistic approach and horizontal implementation.

PAC11 (Security) and PAC8 (competitiveness): cooperation with Croatian PA 8 PAC and  close exchange with the two German PACs of these PAs, and also with Baden-Württemberg, due to the Bavarian overall coordination at the State Chancellery,

Follow-up on the Steering Group work

Meetings: Three Steering Group meetings took place within PA6:

- Kick Off Meeting in Munich (20 June 2011): Constitution of Steering Group, agreement on Rules of Procedures, discussion and agreement (by written procedure) on targets, presentations and discussions on roles and tasks of PACs and Steering Group, discussion and agreement on observers

- 2nd Steering Group Meeting in Zagreb (24 -25 October 2011): discussion and agreement (by written procedure) on targets and labelling procedure, future cooperation, agreement on drafting a matrix on action and shared responsibilities, first open discussion about a stakeholder network as parallel structure to Steering Group

- 3rd Steering Group Meeting in Munich (14 June 2012): report on progress by PACs, discussion and agreement on next steps for finalisation of 1st Report from PACs to European Commission, discussion and agreement on next steps concerning stakeholder network.

Members: The Steering Group members are considered to be representatives from all 14 countries of the Danube Region. The Rules of procedure define the scope, work and participation in the SG of the PA6. Countries nominated focal points coming from the Ministries on national or regional level, related to the PA subject. In case of PA6, focal points are from Ministries responsible for Environment, Nature Protection and Public Health. It is notable that the tasks of the Steering Group members in relation to the EUSDR have to be considered as an “add on” to their daily work, thus the personal and financial capacities for EUSDR related work are in some cases limited, which prevents some of the Steering Group members to participate in the respective meetings. Due to the limited participation of national contacts at the SG meeting, especially by non MS, SG at 2nd meeting endorsed the proposal for sending the letter by PAC to the High Level Group to take action for endorsement of stronger engagement of SG members to the meeting, and if needed nominate new member to the SG.

Table 3: Attendance to Steering Group meetings

| Country* | 1st Meeting 20 June 2011 Munich | 2nd Meeting 24 - 25 Oct. 2011 Zagreb | 3rd Meeting 14 June 2012 Munich |
| --- | --- | --- | --- |
| DE | x | x | x |
| AT | x | x | x |
| CZ |  |  |  |
| SK |  |  | x |
| HU | x | x | x |
| SI |  | x | x |
| HR | x | x | x |
| SRB |  |  |  |
| BIH |  | x |  |
| MNE |  |  |  |
| RO | x | x |  |
| BU |  |  |  |
| MD |  |  |  |
| UA |  |  |  |
| DG ENV | x | x | x |
| DG REGIO | x | x | x |
| PAC4 |  | x |  |
| PAC5 |  |  |  |
| ICPDR |  | x | x |
| Carpathian Convention |  | x |  |

*Austria (AT) , Bosnia & Herzegovina (BiH), Bulgaria (BG), Czech Republic (CZ), Germany (DE), Croatia (HR), Hungary (HU), Moldov (MD), Montenegro (MNE), Serbia (SRB), Slovakia (SK), Slovenia (SI), Romania (RO), Ukraine (UA)

Observers and Other Participants: In the advisory capacity the PACs from other Priority Areas of the Pillar Environment (PA4 & PA5), representatives of the European Commission (DG Regional Policy and DG ENV) and representatives of the Interact Programme are generally invited to participate in each Steering Group meeting. Additionally, SG Members can propose international governmental and nongovernmental organisations as Observers and grant the participation of these organisations in the meetings of the SG, as far and as long as they a) pursue the goals of the Priority Area 6 of the EU Strategy for the Danube Region according to its targets and action plan and contribute substantially to the work of the Steering Group and the PACs; b) operate in more than one country of the Danube Region; c) are based within the Danube Region as defined by Communication COM (2010) 715 and d) have an agenda (field of activity) that has not yet been sufficiently represented by the other Observer status organisations. At the 1st SG meeting, ICPDR and the Carpathian Convention were accepted as permanent observer to SG upon their request. At the 3rd SG meeting, the role of the NGO´s as permanent observers at SG meetings and their role in stakeholder network were considered.

Stakeholder networks: In order to engage a continuous exchange and to further install regional contact points for PA6 in the Danube Region Countries, the establishment of a stakeholder network with committed persons from NGOs, governmental organisations and other networks is envisaged. The stakeholders shall act as regional contact points for PA6 with various tasks, depending on interest and expertise (project development, partner search, project implementation, networking). Technical Assistance budget might be used to cover some of the stakeholder network´s expenses. It is clear that the Steering Group remains the decision taking body within the organisation framework. The establishment of a stakeholder network was discussed in the third Steering Group meeting, and as direct outcome it was agreed that the PACs will draft an outline on potential tasks of a Stakeholder Network, its structure and members and their relationship to the Steering Group. It is foreseen that the agreed proposal should be discussed directly with the Stakeholders at the occasion of the 1st Stakeholder Workshop.

Stakeholder Workshop: According to the general close cooperation among the Pillar II PACs, it has been agreed that the cooperation should be visible also to the outside. For this reason, it has been agreed among the Pillar II PACs, that the Stakeholder Workshop, which is foreseen for each PA of the EUSDR, shall be planned, organised and implemented jointly by the Pillar II PACs. A joint Stakeholder Workshop has the advantage of the larger quantity of target groups, where a more broad variety of topics will be focussed on. As there are many thematic overlappings, the discussions and workshop sessions can cover the environment-related issues at one time and it is expected that this attracts more interested stakeholder than a strictly PA-focussed event. The joint Pillar II Stakeholder Workshop was originally foreseen to take place in June 2012 in Budapest, linked with the Danube Day. Due to organisational restraints and after discussion among the PACs as well as with DG Regional Policy, it will actually take place in September 2012. The agenda foresees, after introductory expert speeches, two main workshop sessions, divided in three parallel sessions which gives the possibility to change the main focus of the session after the lunch break. The workshop sessions are concretely focussed on emerging projects related to current needs and bottlenecks in the single Priority Areas. The objective is to develop a rough (or even detailed) schedule of next steps with the aim to develop “ready-to-go” project applications or other implementation-oriented strategies. Main target actors are environmental NGOs as well as policy makers from all administrative levels.

Exchange with funding programmes: In order to directly discuss the relationship between EUSDR and relevant funding programmes, PAC6 (BY) initiated a meeting with Imre Csalagovits, Head of the Joint Technical Secretariat from Interreg IVB South East Europe Programme (JTS SEE)  (11 October 2011, Budapest). At this occasion, the foreseen labelling procedure was presented by PAC to the JTS, as well as a draft of a Letter of Recommendation to be issued for labelled projects. Intense discussion was raised about the impact of a Letter of Recommendation issued by PACs and which shall be submitted alongside the main project application to the funding programme. As a result, it became clear that the SEE programme will not change their evaluation criteria within the current funding period. In fact, the Letter of Recommendation does not affect the project evaluation. Another example for the current unclear relationship between EUSDR and funding programme was expressed by the ENPI-CBC Romania - Moldova - Ukraine with letter from 27 April 2012 of Iuliu Bara, Head of Joint Managing Authority, with citation of the programme rules: “Any supplementary information provided by the applicant, modifying or improving the content of the Concept Note initially submitted, will not be considered by the Evaluation Committee”. This reaction was based on a PA6 Letter of Recommendation submitted for a project proposal apparently after the deadline of the CBC programme. The JTS SEE nevertheless stated that the Letter of Recommendation can be an important side information for the members of the Monitoring Committee, which are approving or rejecting project application. As the model of issuing Letter of Recommendation is currently applied by many PACs, it should be taken into consideration that these Letters apparently do not directly affect the decision making process of granting funding to labelled projects. Hence, the relation between EUSDR and EU funding programmes needs to be rearranged and settled for the next funding period from 2014.

Apart from this, it turned out that it is also in the interest of the funding programme SEE to enhance the visibility of funded projects by using the EUSDR momentum and political interest. A further cooperation in this field was agreed upon.

1.2.2. Work on actions and projects

On project level, the expectations are to gain a higher visibility on policy level and to transfer project results to the decision making and policy level. A precondition to achieve this aim is an equal and harmonized level of understanding of the EUSDR and its mechanism.

State of play of projects: PA6 includes a broad variety of 16 actions due to the four main topics (biodiversity, landscapes, air and soils) of the PA. From the beginning, it became obvious that projects on biodiversity and nature protection which are closely linked to the river Danube and its tributaries are starting points for implementation. As one of the first works done, the state of play of projects dedicated to single actions was investigated and in several cases meetings with the project initiators took place. Summing up the experiences made so far in PA6 the concrete and actual work, by implementing projects in the context of the targets and actions, is done by respective environmental institutions and actors (national park and protected area administrations, environmental NGOs, science and educational organisations, partly even individuals) which are highly dependent on funding schemes and funding programmes. The PACs were in several cases approached with high expectations, namely requests for funding e.g. for projects in the action plan or directly linked with actions or targets. For instance, several local and regional NGOs in Bavaria were highly motivated to get funding from PAC/the related ministry for projects and initiatives ready to go but at the same were quite disappointed as they were confronted not only with the “three no” but also with the lack of remaining funds in the current funding period 2007-2013.

However, as proposed by the PAC, a broad understanding could be achieved to properly prepare projects for the next funding period starting in 2014, with the precondition that the macro-regional concept is recognised in the strategic documents on all levels (Common Strategic Framework, Partnership Contracts and Operational programs in EUSDR countries). Taking into consideration EUSDR project financing (PA6 in this particular case) there is the need for including its priority actions in policy development of all relevant funding instruments, such a financial diversity is needed to overcome the issue of limited resources and sensitivity in times of financial crisis and avoid significant dependence on the State Budget.

In dialog with stakeholders it was detected that the level of international/transnational cooperation and the setting of existing networks in the field of biodiversity and nature protection is quite weak, which is a precondition for EUSDR-related activities and a big challenge to steer the process of capacity building. Furthermore, the target groups expressed the lack of the financial capacity to build up new co-operation in short-term.

In order to immediately enter into the implementation phase, mainly projects ready to apply for funding in relevant funding programmes were supported.

1.2.2.1. Mura-Drava-Danube Trans-Boundary Biosphere Reserve:

- Bilateral site (Hungary and Croatia)

Nomination was submitted for the Croatian part of Mura-Drava-Danube on 27 September 2011 (Hungary has submitted nomination in 2010). Following the nomination, three clarification questions from UNESCO were received and response, in line with Hungarian reply, was sent. The decision on accepting the bilateral nomination is expected in July 2012.

- Pentalateral site (Austria, Croatia, Hungary, Serbia and Slovenia)

On 25 March 2011, in an act of environmental leadership and trans-boundary cooperation, the Ministers responsible for Environment and Nature Conservation of Austria, Croatia, Hungary, Serbia and Slovenia signed a Joint Declaration to establish a Trans-Boundary Biosphere Reserve along the Mura, Drava and Danube Rivers. This Declaration paves the way to create the world’s first five-country protected area and Europe’s largest river protection area. On 28 October 2011 in Budapest 1st meeting of the Coordination Board for MDD TBR preparation was held. 2nd Meeting of the International Working Group and Coordination Board for MDD TBR was held on 12 and 13 June 2012 in Kopački rit (Croatia). The Ministerial representatives responsible for Environment and Nature Conservation of all five countries as well as delegates of nongovernmental organizations and partners who provided support, such as IUCN and UNESCO, reported on the activities carried out and discussed further steps towards the establishment of the first transboundary protected area shared within the five countries who are jointly going to manage Europe’s most ecologically important riverine areas: Transboundary Biosphere Reserve “Mura-Drava-Danube”.

1.2.2.2. Danubeparks: Project covers a wide range of actions and general objectives of PA6, and therefore a close liaison between Danubeparks and PA6 was established. The 1st phase of project was already running when EUSDR was endorsed, but actually sought for strong connection with PA6 during preparation and application process of the follow-up project Danubeparks II, which was labelled by PA6 and submitted in the last call of Interreg IVB South East Europe programme.

Beside the thematic implementation of Danubeparks, major approach and also starting point for PA6 is the networking of protected areas and NGOs alongside the Danube in eight Danube Countries. The network of protected areas shall be the basis for further activities and gathers highly committed individuals dedicated to preserving biodiversity and nature protection. By active participation of PAC (BY) at project meetings (2 -3 September 2011, Orth/Donau AT) and Danubeparks Final Conference (27 February 2012 Vienna AT), the cooperation between PA6 and Danubeparks was laid on a solid ground as basis for future initiatives. This should help to overcome deficits regarding number and effectiveness of international networks of relevant NGOs in the Danube Region, which hampers their voice being heard at the decision making and policy level. The EUSDR and specifically PA6 will further strengthen the network by coordinating regional and local initiatives and actors.

1.2.2.3. Green Danube Network and Bavarian Network: The need for international and transnational network of NGOs in the Danube Region as a prerequisite for further joint activities was also confirmed in meetings with other relevant NGOs and organisations working in the field of environment, such as Bund Naturschutz Bayern, Auenzentrum Neuburg a.d. Donau and City of Ingolstadt. As a consequence the project proposal Green Danube Network was developed by NGOs from Bavaria, Austria and Hungary aiming at building an environmental network of up to 109 environmental NGOs from 21 European states, among them all states along the Danube. The project has a direct reference to the EUSDR action plan and has been applied for funding in the EU programme Europe for Citizens.

In order to make the EUSDR/PA6 more visible to the public on local level and also to further network existing initiatives, organisations and NGOs, this international approach is accompanied by regional networking initiatives. As a pilot activity, PAC6 (BY) is currently developing an network of institutes with focus on biodiversity, nature protection and environmental education in Bavaria, which shall be later connected to the international networks and may serve as a blueprint for similar activities in other regions. It is intended to use the existing organisations for information events (PAC informs about state of play in PA6 and EUSDR, and is available for local public consulting) and to further promote the EUSDR / PA6 on local level. The network shall be fully established by end of 2012.

The examples of Danubeparks and Green Danube Network shows that in order to raise their significance, networking seems to be a precondition for environmental NGO´s to bundle their competencies and speak with one voice, similar to the strong back-up by the ICPDR in PA4 and PA5. Necessarily, this leads to a strongly bottom-up driven situation for the implementation of single actions of PA6. The PACs have to consider which projects and initiatives are currently in development and can align these to single actions and / or targets. PAC can support these starting points by labelling and (if needed) by project partner search. Due to currently limited funding opportunities, the major implementation phase of single projects will in regular cases not start before the next funding period from 2014 on. Secondly it has also be stressed that a top-down approach by defining implementation-oriented single steps out of the actions can only be successful if there are actors behind, which have the means, the capacity and the funding to implement the single steps.

1.2.2.4 Danube Sturgeon Task Force: First international meeting of NGOs, scientists and PAC6 (BY) was initiated by PACs and WWF Vienna and took place on 20 January 2012 in Vienna. It marked the Kick-off of the Danube Sturgeon Task Force (DSTF), aiming at developing a strategy with a cluster of projects, measures and initiatives to secure viable populations of sturgeon species in the Danube Region. This initiative bundles loosely existent expertise, strategies and local activities under the framework of PA6 and EUSDR in order to reach the respective target by 2020. During the kick off meeting and in the aftermath, a work programme has been developed with tasks, responsibilities and deadlines for the next steps and for the preparation of next Danube Sturgeon Task Force meeting, scheduled for August 2012 and -most probably- financially supported by Technical Assistance budget from PA6. PAC6 (BY) is member of the DSTF and will provide link to the EUSDR, specifically the policy level and use appropriate measures to enhance the visibility. The DSTF core group exists out of 11 members from 5 countries, whereas the larger network currently has 60 members from 12 countries. During the kick off meeting it has been agreed that due to limited available funding, the time until mid-2014 will be used to carefully prepare a cluster of projects for the next funding period. To keep the DSTF work going until that time, TA Budget shall be used to support DSTF preparatory work (i.e. to reimburse travel costs and costs for hosting on the occasion of a meetings).

The objective of securing viable sturgeon population is not just a matter of biodiversity but is at the same time interlinked to other priority areas of the EUSDR like water quality, permeability of habitats, economic development, environmental education and even prevention of crime (related to illegal caviar trade). The sturgeon therefore is a flagship species and indicator for the environmental condition of the Danube River and this initiative has potential to become a flagship activity in the environmental pillar of the EUSDR.

1.2.2.5. SONDAR - Soil Strategy Network in the Danube Region: Project is currently funded by SK-AT Crossborder European Territorial Cooperation programme in its initial phase. Currently, political and public awareness on soil protection issues is considered to be rather low. The project specifically would like to use the momentum of the political commitment of the EUSDR to raise the awareness to the issue. The core activities stem from an international network from regional policy level, scientists and NGOs with focus on soil protection and sustainable development. PAC6 (BY) took part in the SONDAR conference “Soil Protection and Sustainability in the Danube Region” (28 March 2012, St. Pölten, AT) and presented the background and approach of PA6 and EUSDR. A close cooperation in terms of awareness building, enhancing visibility was agreed and as a concrete result, the “Soil protection days” (Bodenschutztage) in Markredwitz (BY) are expected to pick up the issue of SONDAR, EUSDR and public awareness as key topic in the upcoming event in autumn 2014.

1.2.2.6. Other project events and meetings in the reporting period

13 October 2011: Meeting with Bund Naturschutz Bayern, Landesbund für Vogelschutz to discuss status of projects Blue Ribbon of Biodiversity (mentioned in the action plan), Green Danube Network, Treasures of Danube, commitment of close cooperation among the NGOs and PA6.

15 April 2011 and 13 April 2012: Meeting at Auenzentrum Neuburg e.V. to discuss expectations and opportunities by EUSDR / PA6 to NGOs and environmental department on local level in the upcoming years. Close cooperation foreseen especially concerning international contacts, fund raising and public events. Auenzentrum is project partner of Danubeparks II (currently under evaluation). April 2012: Presentation and discussion on PA6 proposal of setting up a stakeholder network.

15 June 2012: Meeting at Haus am Strom, Passau (BY): Presentation and discussion on PA6 proposal of setting up a stakeholder network.

1.2.2.7. Other project contacts: Besides personal meetings, direct electronic exchange has been carried out with organisations currently applying for funding and thus asking for a Letter of Recommendation from PACs as well as with already running projects. The following activities can be mentioned here:

(1) Dr. Zinoviy S. Broyde, Director of Centre "EcoResource", Chernivtsi, Ukraine. Mr. Broyde presented a collection of projects under application or development and asked for a Letter of Recommendation. After alignment of the individual projects to the different PA´s, the project SMIWASTRES was labelled by PA6 Steering Group and received a letter of recommendation. The project however has not been approved by the ENPI Joint Operational Program “Romania-Ukraine-Republic of Moldova”.

(2) Radmila Ustych, Ihor Velykopolsky, NGO FORZA, 88018 Uzhogrod, Ukraine. The project FISH applied for a Letter of Recommendation by PA6 and received it after SG decision.

## Funding

Challenges: Funding is crucial to give life to EUSDR / PA6 related initiatives and emerging projects. As commonly known, EUSDR started in the last two years of the current funding period 2007-2013. To this time, most of the main funding programmes are exhausted or were undergoing or preparing their last calls for projects, for which in many cases it was too late for new project developments. The limited funding opportunities impose the main impediment of keeping the EUSDR momentum and interest of the stakeholder. Regardless some communications that funding is vastly available in the Danube Region on national level, no systematic mechanism to get access to these “hidden” funding could be identified so far. As a consequence, main attention to align funding to labelled projects had been given to the well known EU funding programmes, mostly the European Territorial Cooperation (ETC) programmes in general and here the South East Europe Programme as the most prominent one. As described before, the relation between EUSDR and labelling of projects is not clear so far but needs to be formally developed for the upcoming funding period, starting from 2014.

Apart from these challenges, the support by Interact was highly welcomed. Interact provided an overview on the ETC, IPA CBC and ENPI CBC programmes in the Danube Region, as well as Information on Objective 1 and Objective 2 Programmes and other relevant funds and instruments. Unfortunately it was not possible to gain an overall overview on the remaining funds for the single programmes, these information were requested by PAC6 (BY) on case-by-case basis, related to planned activities and regional focus. Furthermore, the existing and identified funding programmes are different in their character. Actually, there is no one-stop shop programme for the EUSDR / PA6-related project. Hence it has to be investigated case-by-case basis, which programme fits best to the foreseen action / project.

As regards the type of funding, it has to be noted, that for the topics and project holders of PA6, currently the traditional funding programmes as ETC, Life environment, IPA and FP7 are considered to be appropriate. High investment funds are apparently foremost used for economical and transport related issues. Funding for nature protection and environmental issues is foremost classical project funding. It also has to be considered that most of the potential projects need to have an at least cross-border, if not transnational focus, which narrows the number of potential funding programmes.

All in all, funding opportunities for PA6 needs to be identified on a case-to-case basis, depending on the type of project concerning topic, methodology, partnership, regional focus. Funding for PA6 related projects will be very limited until the next funding period. This contradicts the demand of quick and visible results and “success”.

Alternative solutions:

- To overcome the time gap until 2014, it seems to be reasonable to plan and prepare top quality projects in cooperation with the potential project holders “ready to go”, in order to meet the conditions for their financing starting from 2014 (see e.g. example of Danube Sturgeon Task Force). By this, the momentum and interest of the stakeholders and potential project holders in the EUSDR / PA6 can be kept as well and links to policy level can be further established.

- There is however the need to make smaller steps possible. Small scale preparation activities therefore shall be funded already now. A reallocation of still available funds might be a solution (Interact, COM). Technical Assistance budget dedicated to PACs will partly be used for that purpose as well.

- PAC-Activities which do not need extra funding should be considered as appropriate and appreciated work (and “success”) in the meantime. These activities include stock-taking and post-labelling, networking, project preparation, Information & Publicity (workshops, conferences, documents), further affords to establish a sound overall EUSDR implementation structure, seek exchange and collaboration with funding programmes in their programming phase.

Financing of EUSDR in new programming period 2014-2020: In order to fully valorise the high potential of the EUSDR, the alignment of funding from the various EU funding programmes remains one major challenge. In order to create funding opportunities to support PA6-related projects in the next programming period, Member States in the preparation of the Partnership Agreements and the Operational Programmes should take the EUSDR targets for preservation of biodiversity, landscapes and the quality of air and soils into account. Priority settings should be addressed in these documents.

Labelling system in new programming period 2014-2020: The labelling system and the method of issuing a Letter of Recommendation have been established in many EUSDR Priority Areas. However, the relationship between the EUSDR and the funding programmes as well as the impact of a Letter of Recommendation to the project evaluation systems and selection criteria could not been clarified in a satisfactory way so far. As it is a sensitive issue, it should be strived for a solution that the funding programmes can keep their own identity and their own specific objectives but nevertheless their relationship to the EUSDR is clearer. In this respect, the EUSDR could also be an opportunity to harmonize the existing funding programmes, as the strategy provides a common roof and vision for the entire region, under which the EU funding programmes can orient themselves. On operative level, the labelling procedure and specifically the impact of a Letter of Recommendation should be clarified. In case that the LoR shall have a direct influence on the evaluation score of the respective programme, a need harmonized and agreed labelling criteria among all PACs would become necessary. Facing the fact that the programming phases are starting in many major EU funding programmes in 2012, it is of urgent importance, that stakeholders from the EUSDR (e.g. PACs, Interact, NCPs) are involved in these processes to ensure, that the relationship is clarified in the next funding period. It is important that MS recognise the importance to involve PACs in the programming process for the next programming period and both PACs from PA6 are offering respective engagement.

Technical Assistance: Due to the current difficult funding situation and the intention to focus on support of high quality project preparation, PAC6 (BY) decided to dedicate parts of the granted Technical Assistance budget for this purpose. After exchange with relevant and active NGO´s it became obvious that there is a clear need and demand to facilitate project preparation activities by granting financial support to relevant preparation meetings and workshops. By this, parts of the TA budget can be used to directly support emerging projects and initiatives and also to keep the momentum and interest of these actors in the PA6 and EUSDR in general. In order to meet the requirements of the proper and transparent use of TA means by third parties, PAC6 (BY) developed a fact sheet with a general description and eligibility rules for third parties in case they would like to make use of this possibility. Specifically, the Danube Sturgeon Task Force and the foreseen second meeting in August 2012 in Tulcea (RO) is one actual example for this purpose. It will be decided on case-to-case basis by the PAC (BY), if budget will be granted to respective applicants. In parallel, an external service provider will be contracted as an auditor and as paying body (see also Annex).

1.4 Publicity Measures and Visibility

Publicity Measures: Thanks to Interact, an overall EUSDR-Website has been put to place at www.danube-region.eu with specific sections for each PA. This is considered to be very useful, as it provides a common umbrella for all PA´s. In addition, an information section about the Coordinating Role of the Bavarian State Ministry of the Environment and Public Health has been established  with contact information of the PAC6 (BY). An information portal for the EUSDR has been established on regional level for Bavaria by the Bavarian State Chancellery. HR in the PAC role also provides relevant EUSDR PA6 information on its website.

Publications: Linked with the need to strengthen the links of the PAC with stakeholders on all levels but especially with local and regional NGOs, PAC6 (BY) developed an information- and service flyer (see draft in Annex) with a description of the background of EUSDR, the Environmental Pillar II and the Priority Area 6. The flyer is a short and comprised information “to take away” which will be translated in all Danube Region languages (and English) and which shall be distributed by Steering Group members directly, as well as at various events. Beside the key information, a direct service offer and description “what can the PAC do for you” including contact information of the two PA6 PACs is included, in order to enable and motivate stakeholders and project developers to get into direct contact with the PACs. The flyer shall be ready for distribution by September 2012 and is financed by PA6 (BY) Technical Assistance budget.

As a second publication funded by the TA budget, a project brochure is planned. The brochure shall present selected “good practice” projects related to the PA6 topics and covering parts of the entire Danube Region. The brochure shall highlight the existing initiatives and projects, as well as point out future activities, and at the same time shall reflect the benefit of the EUSDR as a common umbrella. The English brochure shall be published in late 2012 or early 2013.

## Next steps

The following next steps are foreseen until end of 2012:

PAC-internal work plan:

- Drafting a PA6 work plan until end of 2013

- Further strengthen cooperation among Pillar II PACs

- Further cooperation with other PACs (e.g. PA1a, PA4, PA8, PA9), highlighting horizontal approach of EUSDR, also to keep the momentum.

PAC - Steering Group – Stakeholder relation:

- Discussion on future tasks and definition of Steering Group and stronger involvement of Stakeholder. Directions for further work have been set out at 3rd Steering Group Meeting on 14 June 2012.

- Further scoping of existing and emerging networks and organisation and linking them under umbrella of EUSDR / PA6 (e.g. Danubeparks, Green Danube Network, Danube Sturgeon Task Force).

- Establishment of links of these networks (or of representatives) to policy level.

Project level:

- Project development with stakeholders and networks, meetings partly funded by TA budget (example: 2nd Danube Sturgeon Task Force meeting, scheduled for August 2012 in Tulcea).

- In case of project approval, further activities with Danubeparks II project are envisaged and need to be discussed with project holders.

- Monitoring of selected and labelled projects, enhancing their visibility by participation at relevant events and to highlight their contribution to the implementation of EUSDR / PA6

- Establish contacts with identified PA6-related projects Be-Nature, Green Mountain and RAMSAR SK-AT etc.

Public Relations and visibility for PA6

- Preparation and implementation of first joint Pillar II Stakeholder Workshop (September 2012, Budapest)

- Distribution of PAC6 information flyer in all Danube Region languages

- Starting preparation of a project brochure in English language

- Support for 1st Annual Conference in Regensburg

Furthermore, ways should be sought, how PAC-expertise could be introduced in the currently starting programming process for the next funding period, especially for ETC SEE programme. This could be facilitated by Interact. PAC6 (BY) will offer to get involved in this process.

# Progress by targets

State of play: In order to ensure all preconditions for developing the roadmap for the implementation of PA6, following on the conclusions taken on the SG 2 meeting, the draft matrix table was developed by PACs. Matrix table proposed for each action implementation tool, rationale for implementation, milestones, potential related projects, relation to PA6 targets and other EUSDR targets (especially Pillar II), source of funding, deadlines, leading countries and responsible actors. The matrix was circulated to all SG members together with the guidance document in December for adoption of proposed format and updating and calling the SG members to identify themselves as the potential country leader for each action. In addition, the matrix table was used as the baseline for defining the roadmap for PA6. For the most of the actions it was intended that the further work should be done on the following points: source of funding, deadlines, leading countries and responsible actors.

Having in mind that biodiversity related targets deriving from new strategic plan of CBD and EU 2020 biodiversity strategy in the Annex 1 (Roadmap for PA6), all biodiversity related actions are additionally linked to the targets of EU 2020 biodiversity strategy. List of actions related to specific PA6 target, along with the short summary of the progress in their implementation and list of associated projects, is provided bellow:

## 2.1. Target: To halt the deterioration in the status of all species and habitats covered by EU nature legislation and achieve a significant and measurable improvement, adapted to the special needs of the Danube Region by 2020.

### “To contribute to the 2050 EU vision and 2020 EU target for biodiversity”.

### “To manage Natura 2000 sites and other protected areas effectively”

### “To protect and restore most valuable ecosystems and endangered animal species”

### “To decrease the input of pesticides into the environment of the Danube Region"

### “To decrease air pollutants”

### “To raise awareness of the general public, by acknowledging and promoting the potentials of natural assets as drivers of sustainable regional development”

### “To educate children and young people”

### “To build capacities of local authorities in the environment-related matters”

- Progress in the implementation of the action:

- The milestones for the proposed actions have been developed following the activities proposed by EU 2020 biodiversity strategy, especially regarding the adoption of the new legislative framework and existing obligations deriving from the environmental aquis. This approach was taken in order to avoid the additional reporting requirements from countries especially MS and in order to establish stronger cooperation with sectorial DG (DG ENV).

- List of projects associated with the actions,:

- Danubeparks II (Interreg IVB South East Europe Programme) Countries involved: AT, DE, SK, HU, SRB, BUL, RO

- Fish: joint basin – joint solutions (ENPI Hungary-Slovakia-Romania-Ukraine program) Countries involved: UA, SK

- Green Danube Network (“Europe for Citizens” Programme) Countries involved: DE, AT, HU

- Protecting “Europe’s Lifeline” - The creation of a Trans-Boundary UNESCO Biosphere Reserve along the Danube, Drava and Mura Rivers (TBR MDD) WWF Project

## Target: By 2020, ecosystems and their services are maintained and enhanced by establishing green infrastructure and restoring at least 15% of degraded ecosystems, including degraded soils.

### “To develop green infrastructure in order to connect different bio-geographic regions and habitats”

### “To ensure appropriate treatment of solid waste”

### “To create standardised and compatible information on land cover on transnational basis”

### “To raise awareness about soil protection”

### “To contribute to the 2050 EU vision and 2020 EU target for biodiversity”.

### “To prepare and implement transnational spatial planning and development policies for functional geographical areas (river basins, mountain ranges etc.)”

- Progress in the implementation of the action:

- The milestones for the proposed actions have been developed following the activities proposed by EU 2020 biodiversity strategy, especially regarding the adoption of the new legislative framework and existing obligations deriving from the environmental aquis. This approach was taken in order to avoid the additional reporting requirements from countries especially MS and in order to the established stronger cooperation with sectorial DG (DG ENV).

- List of projects associated with the action,:

- SMIWASTRES (Joint Operational Program "Romania-Ukraine-Republic of Moldova" 2007-2014.) Countries involved UA and MD

- SONDAR - Soil Strategy Network in the Danube Region (Interreg IVA HU - AT Interreg IVA SK – AT) Countries involved: AT, HU, SK, CZ

- Bioregio Carpathians (ERDF; IPA, Interreg IVB South East Europe Programme); Countries involved: AT, CZ, HU, RO, SK, SRB, UA as well as IT, PL

- “Wetland restoration in the Mura-Drava-Danube area”  WWF Project

## Target: Secure viable populations of Danube sturgeon species and other indigenous fish species by 2020.

### "To explore together the appropriateness of reviewing the Convention Concerning Fishing in the Waters of the Danube".

### “To protect and restore most valuable ecosystems and endangered animal species”

- Progress in the implementation of the action:

- Long-term strategy on the conservation of Sturgeon Species in the Danube shall be developed based on initiatives of WWF, IAD and other NGOs and networks, (concussions form the 1st meeting, December 2012). Follow up on the progress by PAC is needed, it should be considered the possibility to use TA Budget for preparation of the activities.

- List of projects associated with the action:

- Sturgeon 2020 : Countries involved: DE, AT, HU, RO, SRB (Core Group)

## Target: By 2020, Invasive Alien Species and their pathways are identified and prioritised, priority species are controlled or eradicated, and pathways are managed to prevent the introduction and establishment of new Invasive Alien Species.

### “To reduce the spread of invasive alien species (IAS)”

- Progress in the implementation of the action:

- To order to have the uniformed legislative framework for combating and controlling the IAS in EUSDR region it was agreed to follow on the new EC legislative instrument to develop policy gaps in combating IAS (to be developed 2012 )

- List of projects associated with the action: no new project information in this reporting period

ANNEXES

Annex 1: Roadmap

Annex 2: Projects

Annex 3: Joint Declaration by the high level country representatives responsible for the coordination of the Pillar ‘Protecting the Environment in the Danube Region.

Annex 4: Project Data Sheet

Annex 5: Fact Sheet on Labelling process

Annex 6: EUSDR - PA6 - Eligibility Rules

Annex 7: Draft of Service - and Information Flyer

This Report on implementation of the EUSDR Priority Area 6 to preserve biodiversity, landscapes and the quality of air and soils, prepared by PAC 6 (BY and RH) and endorsed by the Steering Group members at its 3rd  meeting (Munich, 14 June 2012), is submitted to the European Commission (DG REGIO and DG ENV). Integral part of this report are Annexes as follows: Annex1: Roadmaps to implement each action; Annex 2: Projects approved by the Steering Group; Annex 3: Joint Declaration by the high level country representatives responsible for the coordination of the Pillar ‘Protecting the Environment in the Danube Region; Annex 4: Project Data Sheet; Annex 5: Fact Sheet on Labelling process; Annex 6: EUSDR - PA6 - Eligibility Rules; Annex 7: Draft of Service- and Information Flyer.

Joint Declaration by the high level country representatives responsible for the coordination of the Pillar ‘Protecting the Environment in the Danube Region Annexed to the Report

In Germany regular meetings and exchange took place in Bavaria with Bavarian State Chancellery, PAC 11 (BY), State Ministry Baden-Württemberg, PAC 08 (Bad.-W.), Federal Ministry for Environment, Nature Protection and Nuclear Safety (PAC for Biodiversity in EUSBR) and Federal Foreign Office, acting as National Contact Point.

http://www.imo.hr/files/report-danube-strategy-1.pdf

1st Labgroup meeting in Vienna (16 -17 March 2011); 2nd Labgroup Meeting, Budapest(14-15 June 2011)

1st conference of EUSDR with PACs, National Coordinators and EU COM in Gödöllö (HU) (8-10 May 2011)

Danube Summit and political kick-off meeting of the responsible ministries of Pillar II (Environment) of the EUSDR on 26 May 2011 in Niederalteich (Bavaria)

According to the Law on Organisation and Scope of Ministries and other Central State Administration Bodies (Official Gazette No. 150/11, 22/12)

High Level Group: EU Strategy for the Baltic Sea Region and EU Strategy for the Danube Region

(21 November 2011, Brussels)

http://www.southeast-europe.net/en/

Cross-Border Cooperation within the European Neighbourhood and Partnership Instrument (ENPI)

Session of the International Advisory Committee for Biosphere Reserves which considered nominations was held 2 to 4 April 2012.

Action 10 of PA4: To reduce existing water continuity interruption for fish migration in the Danube river basin

http://www.danube-region.eu/pages/objective-3-ipa-cbc-and-enpi-cbc-programmes

http://www.stmug.bayern.de/eu/regional_zusammenarbeit/argealp.htm#donaustrategie (in German)

http://www.bayern.de/Donaustrategie-.2570/index.htm (in German)

http://www.zastita-prirode.hr/Aktivnosti-projekti-i-medunarodna-suradnja/Aktivnosti/Strategija-EU-za-dunavsku-regiju-prioritetno-podrucja-6.-Ocuvanje-bioloske-raznolikosti-krajobraza-te-kvalitete-zraka-i-tla (in Croatian); http://www.zastita-prirode.hr/eng/Projects-International-Cooperation/International-Cooperation-and-European-Union/Activities/EU-Strategy-for-the-Danube-Region-Priority-Area-6-to-preserve-biodiversity-landscapes-and-the-quality-of-air-and-soils (in English)

Full description is provided in Annex 2 of this Report

Projects identified by desk research to contribute to this target, but no contact established in this reporting period: Be-Natur (ERDF, IPA, Interreg IVB South East Europe Programme) (Countries involved AT, BG, HU, RO, SRB as well as GR, IT ) RAMSAR SK - AT (Interreg IVA SK - AT Programme) (Countries involved AT, SK / Morava - Thaya Floodplains)

http://www.ptice.hr/dokumenti/2011_FS%20MAVA_engl.pdf

Due to the complexity of action and means of achievement, keep this action under 2 targets

Full description is provided in Annex 2 of this Report

Projects identified by desk research to contribute to this target, but no contact established in this reporting period: Green Mountain (ERDF; IPA¸Interreg IVB South East Europe programme) Countries involved: AT, BA, BG, GR (1), HU (1), IT (2), ME, RO, SK as well as GR, IT

http://awsassets.panda.org/downloads/letak_eng.pdf

Due to the complexity of action and means of achievement, keep this action under 2 targets

Full description is provided in Annex 2 of this Report